## Slide 1: Just Force
Team Git Gu(i)d
Joey Tong – Lead
Anthony Olivares – Design
Connor Cummings – Interface
Austin Ford -- Architect

## Slide 2: Our Game
Top-Down Skill based shooter game
Similar to “Hotline Miami”
The player must kill enemies to proceed to the next level.
Skills, weapons, and item pickups are made available to the player
The game is set in the mid 20th century and is about a detective that goes on a rampant killing spree to rid his hometown of criminals.

## Slide 3: What Went Right?
Reserved about 1/3 of the semester for delays and setbacks, this proved to be spot on. No “Crunch Time” required. Most of development was very smooth and consistent despite having to overcome many issues.
We were able to meet or exceed all of our core objectives and most of our secondary/tertiary objectives
From day 1 we wanted the game to play well and be responsive, that is perhaps the biggest success of the game.
Halfway through the semester, we decided to have weekly, in person meetings. This proved to be very useful for the group.
Controls are very responsive
Game has no major lag issues
Interface works without flaws

## Slide 4: What Went Right? (Cont)
Visual Assets turned out as planned at the start.
Map Editor proved to be very useful and fairly easy to use, despite the difficulty of making it.
Gameplay is challenging, as we planned for.
The pace of the game is relatively fast
The code is neatly organized into many classes and folders, avoiding a monstrous main game loop.
Interface visuals look clean

## Slide 5: What Went Wrong?
Many things went wrong, none of which we could not overcome.
Lack of communication towards beginning of development.
Several fatal optimization issues that were difficult to detect
AI proved to be very complex
Austin fell very ill near the end of the semester. Was hospitalized, setting us back slightly for milestone 3. We made up for time afterwards.
Anthony missed deadlines several times. But managed to produce a good final product in the end. Ideally, Anthony would have worked on the code much more if design deadlines were met.
Some tertiary objectives proved to be out of reach, such as particle effects and bosses. Not critical to the game experience though.

## Slide 6: What Went Wrong? (Cont)
We encountered many errors while implementing File Loading and Saving to .dat files for maps that required hours of debugging and testing to fix.
We had a small incident where a forced merge overwrote some changes to the repository which was remedied with git commands.
Some parts of the UI were not properly scaled, easy fix.
Rotating sprites proved to be very confusing due to how XNA handles rotation (-pi ~ +pi) Caused lots of frustration when first implementing graphics
An indexing issue in the pathfinding code caused a severe optimization error that took several hours of debugging to fix.
Map Editor code was poorly structured causing some issues with implementing new functions.

## Slide 7: Major Challenges We Overcame
1. Movement: We wanted movement that “feels good” (Joey & Connor)
The Solution: Vector thrust movement that records velocity and updates based on current velocity. This gives the player acceleration and deceleration when moving.
2.Collision: Rectangle Object’s methods/properties were insufficient (Austin)
The Solution: We hard coded methods that would check for intersections in rectangles using our proprietary “Coord” object type which stores more precise coordinates (doubles)
3. Optimization (Editor): Fatal flaw that caused massive lag (Joey & Connor)
The Solution: It turns out some texture files were 1000x1000 causing the program to do many unnecessary calculations resizing the images.
4. GameStates: We had trouble doing gamestates (Connor)
The solution: Instead of using Enums, which we had not learned at the time, I (Joey) sat down with Connor and we coded a gamestate manager helper class that matched strings to certain game states. Everything was done from scratch to gain a better understanding of the purpose of a GameState manager.

## Slide 8: What we would have changed
The Map editor code is very messy, every new value added to tiles is stored in a new and separate 2D array instantiated manually. We should have created more helper classes to store data more cleanly and supports implementing new features more easily.
The AI does not actually check for collision, the pathfinding merely makes sure it never takes a path that collides with objects. This should be changed if the AI were made more dynamic/intelligent. The AI also does not check if there are objects in its vision, so it can see the player through solid walls.
The system for adding new textures to the editor requires too much manual work. An automated system or a simpler system would have been much better.
The debug console is kind of an afterthought, it does not have many commands and is not very straightforward to access.
The GameStateManager is prone to exceptions since it uses strings instead of Enums.
The skills are not particularly useful or essential to the gameplay. We should have designed and balanced this more carefully.

## Slide 9: What did we learn?
Everyone learned to use basic git commands and adding to the changelog
Joey - AI programming, team management, source code management, game designing and balancing
Austin - File IO, collision detection, parent/child classes and code structural coding, optimization, sound, code organization.
Anthony - Game Design, level design, play testing, asset implementation, File IO
Connor - UI design, movement, gamestates, control mapping, creating map editing tools, optimization
In short: We learned mostly everything we coded in the game (duh)

## Slide 10: Conclusion
As a group, we are very proud of our game.
We achieved most of the goals we set out for ourselves, and the final game looks almost identical to the initial sketches we made at the beginning of the semester.
Since our code base is so large (4000+ lines) we don’t remember a lot of the things we did towards the beginning. The changelog (readme.md) on the repository was very helpful.
We worked well as a team and managed to push out a product that we can confidently put our name on. Despite its flaws, Just Force was a major success and great learning experience.